## Requirement_Traceability_Matrix
CAMPUS SMART TECHNOLOGY
REQUIREMENTS TRACEABILITY MATRIX
Project Name: |  | Campus Smart ERP
Project Manager Name: |  | Eng. Hany Shebl
Project Description: |  | Develop a full ERP system
|  | BRD |  | FSD |  | STATUS
ID | Business Requirement ID# | Business Requirement / Business Use case | Functional Requirement ID# | Functional Requirement// Detail | Development Status | END DATE | Tested In | Technical Specification | Additional Comments | Approve Date
| Mod1 | Basic Forms Module | Mod1.1 | Company Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod1.2 | Branches Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod1.3 | Years Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod1.4 | Countries Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod1.5 | City Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  |  | Banks Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  |  | Bank Branches Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  |  | Bank Accounts Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  |  | School Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  |  | Stages Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod1 Testing |  | In Progress
| Mod2 | Bus Module | Mod2.1 | Bus Main info Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod2.2 | Bus Ways Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod2.3 | Bus Drivers Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod2.4 | Bus Price List Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod2.5 | Bus Discounts Form (Add/Edit/Delete) | Completed | 2017-10-15
|  |  | Mod2.6 | Bus Occopation | Completed | 2017-10-15
|  |  | Mod2.8 | Bus Complains and Monitoring Form | In Progress
|  |  | Mod2.9 | Bus Reports | In Progress
|  |  | Mod1 Testing |  | In Progress
| Mod3 | Student Registeration | Mod3.1 | Student info & Img Form (Add/Edit/Delete) | Completed | 2017-10-25
|  |  | Mod3.1 | Student Configuration Form | Completed
|  |  | Mod3.1.1 | >> Main Fees and discount | Completed
|  |  | Mod3.1.2 | >> Books Fees and discount | Completed
|  |  | Mod3.1.3 | >> Uniform Fees and Discount | Completed
|  |  | Mod3.1.4 | >> Transportation Fees and discount | Completed
|  |  | Mod3.1.5 | >> Student Fees Types | Completed
|  |  | Mod3.1.6 | >> Other Comments | Completed
| Mod4 | Financial Module | Mod4.1 | Analysis | Completed | 2017-10-26
|  |  | Mod4.2 | Design | Completed
|  |  | Mod4.3 | Development | Completed
|  |  | Mod4.4 | Accounting Guide | Completed
|  |  | Mod4.4.1 | Assets أصول | Completed
|  |  | Mod4.4.2 | Discounts خصوم | Completed
|  |  | Mod4.4.3 | expenses مصروفات | Completed
|  |  | Mod4.4.4 | income ايرادات | Completed
|  | Accounting Details Forms | Mod4.5 | Accounting Tree (Add/Edit/Delete) | Completed | 2017-11-02
|  |  | Mod4.5.1 | Sub Accoutnig Tree (Add/Edit/Delete) | Completed | 2017-11-08
|  |  | Mod4.5.2 | Daily Jornal | Completed | 2017-11-14
|  |  | Mod4.5.3 | Ledger | Completed | 2017-11-20
|  |  | Mod4.5.4 | Trial Balance | Completed | 2017-11-22
|  |  | Mod4.5.5 | Recive statements | Completed | 2017-11-26
|  |  | Mod4.5.6 | BankDeposit ,Withdrow | Completed | 2017-11-26
|  |  | Mod4.5.7 | Permission for cash Debit ,Credit | Completed | 2017-11-28
|  |  | Mod4.5.8 | Cost centers / Reports | Completed | 2017-12-03
|  |  | Mod4.5.9 | Account statement | Completed | 2017-12-06
|  |  | Mod4.5.10 | Main treasury | Completed | 2017-12-10
|  |  | Mod4.5.11 | Sub Treasury | Completed | 2017-12-14
|  |  | Mod4.5.12 | Treasury Reports | Completed | 2017-12-20
|  |  | Mod4.5.13 | Expenses | Completed | 2017-12-24
|  |  | Mod4.5.14 | Expenses Registration | Completed | 2017-12-26
|  |  | Mod4.5.15 | Cash Recivable -payable | Completed | 2017-12-31
|  |  | Mod4.5.16 | Note Recivable -payable | Completed | 2018-01-03
|  |  | Mod4.5.17 | cheque Recivable -payable | Completed | 2018-01-06
|  |  | Mod4.5.19 | Dedecation & bonus | Completed | 2018-01-10
|  |  | Mod4.5.20 | income statement | Completed | 2018-01-14
|  |  | Mod4.5.18 | First Balance | Completed | 2018-01-22
|  |  | Mod4.5.21 | Expensex Reports | In Progress | 2018-03-15
|  |  | Mod4.5.22 | Journal -Entry Report | In Progress | 2018-03-15
|  |  | Mod4.5.23 | ledger account report | In Progress | 2018-03-15
|  |  | Mod4.5.24 | trial Palance report | In Progress | 2018-03-15
|  |  | Mod4.5.25 | receipt / exchange reports | In Progress | 2018-03-15
|  |  | Mod4.5.26 | account statement repoer | In Progress | 2018-03-15
|  |  | Mod4.5.27 | Treasury Reports | In Progress | 2018-03-15
|  |  | Mod4.5.28 | check deposit withdrow perort | In Progress | 2018-03-15
|  |  | Mod4.5.29 | visa transaction Report | In Progress | 2018-03-15
|  |  | Mod4.5.30 | Bus Expenses Report | In Progress | 2018-03-15
|  |  | Mod4.5.31 | Cost centers reports | In Progress | 2018-03-15
|  |  | Mod4.5.32 | Student Account ,payment Report | In Progress | 2018-03-15
TESTING
Run
| Mod5 | HR Module | Mod5.0 | Analysis | Completed
|  |  | Mod5.1 | Employees | Completed
|  |  | Mod5.2 | Salary Types | Completed
|  |  | Mod5.3 | Employee Salary | Completed
|  |  | Mod5.4 | Monthly Salary | Completed
| Mod6 | Privilages Module | Mod5.6 | Groups | Completed
|  |  | Mod5.7 | Users | Completed
|  |  | Mod5.8 | User Privlages | Completed
|  |  | Mod5.9 | Resources & Multilanguage | Completed
| Mod7 | Inventroy Module | Mod6.1 | Analysis | In Progress
Note on A7: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B7: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C7: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on E7: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on F7: • Status: This column should be populated with the current status of the functional requirement.
Note on G7: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on H7: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on I7: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.