## Requirement_Traceability_Matrix
CAMPUS SMART TECHNOLOGY
REQUIREMENTS TRACEABILITY MATRIX
Project Name: |  | Campus Smart ERP
National Center: |  | <required>
Project Manager Name: |  | Eng. EMAD ABD EL KAWY
Project Description: |  | Develop a full ERP system
|  | BRD |  | FSD
ID | Business Requirement ID# | Business Requirement / Business Use case | Functional Requirement ID# | Functional Requirement// Detail | Development Status | END DATE | Tested In | Implemented In | Additional Comments
001 | Mod1 | Basic Forms Module | Mod1.1 | Company Form (Add/Edit/Delete) | Completed | 2017-10-15
002 |  |  | Mod1.2 | Branches Form (Add/Edit/Delete) | Completed | 2017-10-15
003 |  |  | Mod1.3 | Years Form (Add/Edit/Delete) | Completed | 2017-10-15
004 |  |  | Mod1.4 | Countries Form (Add/Edit/Delete) | Completed | 2017-10-15
005 |  |  | Mod1.5 | City Form (Add/Edit/Delete) | Completed | 2017-10-15
008 |  |  |  | Banks Form (Add/Edit/Delete) | Completed | 2017-10-15
009 |  |  |  | Bank Branches Form (Add/Edit/Delete) | Completed | 2017-10-15
010 |  |  |  | Bank Accounts Form (Add/Edit/Delete) | Completed | 2017-10-15
011 |  |  |  | School Form (Add/Edit/Delete) | Completed | 2017-10-15
012 |  |  |  | Stages Form (Add/Edit/Delete) | Completed | 2017-10-15
013 |  |  | Mod1 Testing |  | In Progress
014
015 | Mod2 | Bus Module | Mod2.1 | Bus Main info Form (Add/Edit/Delete) | Completed | 2017-10-15
016 |  |  | Mod2.2 | Bus Ways Form (Add/Edit/Delete) | Completed | 2017-10-15
017 |  |  | Mod2.3 | Bus Drivers Form (Add/Edit/Delete) | Completed | 2017-10-15
018 |  |  | Mod2.4 | Bus Price List Form (Add/Edit/Delete) | Completed | 2017-10-15
019 |  |  | Mod2.5 | Bus Discounts Form (Add/Edit/Delete) | Completed | 2017-10-15
018 |  |  | Mod2.6 | Bus Complains and Monitoring Form | In Progress
018 |  |  | Mod2.8 | Bus Reports | In Progress
020 |  |  | Mod1 Testing |  | In Progress
021
022 | Mod3 | Student Registeration | Mod3.1 | Student info & Img Form (Add/Edit/Delete) | Completed | 2017-10-25
023 |  |  | Mod3.1 | Student Configuration Form | Testing
024 |  |  | Mod3.1.1 | >> Main Fees and discount | Completed
025 |  |  | Mod3.1.2 | >> Books Fees and discount | Completed
026 |  |  | Mod3.1.3 | >> Uniform Fees and Discount | Completed
027 |  |  | Mod3.1.4 | >> Transportation Fees and discount | Completed
028 |  |  | Mod3.1.5 | >> Other Comments | In Progress
029
022 | Mod4 | Financial Module | Mod4.1 | Analysis | In Progress
|  |  | Mod4.2 | Design | In Progress
|  |  | Mod4.3 | Development | In Progress
|  |  | Mod4.4 | Accounting Guide
|  |  | Mod4.4.1 | Assets Form (Add/Edit/Delete)
|  |  | Mod4.4.2 | Discounts Form (Add/Edit/Delete)
|  |  | Mod4.4.3 | expenses Form (Add/Edit/Delete)
|  |  | Mod4.4.4 | income Form (Add/Edit/Delete)
| Mod5 | Accounting Module | Mod5.1 | Accounting Tree (Add/Edit/Delete) | Completed | 2017-02-11 | done
|  |  | Mod5.2 | Sub Accoutnig Tree (Add/Edit/Delete) | Completed | 2017-06-11 | done
|  |  | Mod5.3 | Daily Jornal entry (Add/Edit) | Completed | 2017-08-11 | done
|  |  | Mod5.4 | Ledger report |  | 2017-09-11
|  |  | Mod5.5 | Trial Palance (Add/Edit/Delete) |  | 13/11/2017
|  |  | Mod5.6 | receipt / exchange statement |  | 14/11/2017
|  |  | Mod5.7 | BankDeposit ,Withdrow |  | 15/11/2017
|  |  | Mod5.8 | Permission for cash Debit ,Credit |  | 16/11/2017
|  |  | Mod5.9 | Cost centers | Completed | 19/11/2017
|  |  | Mod5.10 | Account statement |  | 22/11/201 | done
|  |  | Mod5.11 | Main treasury | Completed | 22/11/2017
|  |  | Mod5.12 | Sub Treasury |  | 23/11/2017
|  |  | Mod5.13 | Treasury Reports |  | 27/11/2017
|  |  | Mod5.14 | Expenses | Completed | 28/11/2017
|  |  | Mod5.15 | Expenses Registration |  | 29/11/2017
|  |  | Mod5.16 | Expenses Reporrts |  | 29/11/2017
|  |  | Mod.17 | Journal -Entry Report | Completed | 30/11/2017
|  |  | Mod5.18 | ledger account report |  | 2017-03-12
|  |  | Mod5.19 | trial Palance report |  | 2017-03-12
|  |  | Mod5.20 | receipt / exchange reports |  | 2017-04-12
|  |  | Mod5.21 | account statement repoer |  | 2017-04-12
|  |  | Mod5.22 | Treasury Reports |  | 2017-05-12
|  |  | Mod5.23 | income statement |  | 2017-05-12
|  |  | Mod5.24 | check deposit withdrow perort |  | 2017-06-12
|  |  | Mod.25 | visa transaction Report |  | 2017-06-12
|  |  | Mod5.26 | Bus Expenses Report |  | 2017-06-12
|  |  | Mod5.27 | Cost centers reports |  | 2017-07-12
|  |  | Mod.28 | Student Account ,payment Report |  | 2017-07-12
|  | test And Quality | Mod2 testing |  |  | 2017-10-12
|  | Revision |  |  |  | 15/12/2017
022 | Mod5 | HR Module | Mod5.1 | Analysis | In Progress
022 | Mod6 | Inventroy Module | Mod6.1 | Analysis | In Progress
031
032
033
034
Note on A8: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B8: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C8: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on E8: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on F8: • Status: This column should be populated with the current status of the functional requirement.
Note on G8: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on H8: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on I8: • Implemented In: This column should be populated with the module that the functional requirement has been implemented in.