## Requirement_Traceability_Matrix
CAMPUS SMART TECHNOLOGY
REQUIREMENTS TRACEABILITY MATRIX
Project Name: |  | Campus Smart ERP
Project Manager Name: |  | Eng. Hany Shebl
Project Description: |  | Develop a full ERP system
|  | BRD |  | FSD |  | STATUS
ID | Business Requirement ID# | Business Requirement / Business Use case | Functional Requirement ID# | Functional Requirement// Detail | Development Status | END DATE | Tested In | Technical Specification | Additional Comments | Approve Date
| Mod1 | Basic Forms Module | Mod1.1 | Company Form (Add/Edit/Delete) | Completed
|  |  | Mod1.2 | Branches Form (Add/Edit/Delete) | Completed
|  |  | Mod1.3 | Years Form (Add/Edit/Delete) | Completed
|  |  | Mod1.4 | Countries Form (Add/Edit/Delete) | Completed
|  |  | Mod1.5 | City Form (Add/Edit/Delete) | Completed
|  |  | Mod1.6 | Banks Form (Add/Edit/Delete) | Completed
|  |  | Mod1.7 | Bank Branches Form (Add/Edit/Delete) | Completed
|  |  | Mod1.8 | Bank Accounts Form (Add/Edit/Delete) | Completed
|  |  | Mod1.9 | School Form (Add/Edit/Delete) | Completed
|  |  | Mod1.10 | Stages Form (Add/Edit/Delete) | Completed
|  |  | Mod1 Testing |  | In Progress
| Mod2 | Bus Module | Mod2.1 | Bus Main info Form (Add/Edit/Delete) | Completed
|  |  | Mod2.2 | Bus Ways Form (Add/Edit/Delete) | Completed
|  |  | Mod2.3 | Bus Drivers Form (Add/Edit/Delete) | Completed
|  |  | Mod2.4 | Bus Price List Form (Add/Edit/Delete) | Completed
|  |  | Mod2.5 | Bus Discounts Form (Add/Edit/Delete) | Completed
|  |  | Mod2.6 | Bus Occopation | Completed
|  |  | Mod2.8 | Bus Complains and Monitoring Form | In Progress
|  |  | Mod2.9 | Bus Reports | In Progress
|  |  | Mod1 Testing |  | In Progress
| Mod3 | Student Registeration | Mod3.1 | Student info & Img Form (Add/Edit/Delete) | Completed
|  |  | Mod3.1 | Student Configuration Form | Completed
|  |  | Mod3.1.1 | >> Main Fees and discount | Completed
|  |  | Mod3.1.2 | >> Books Fees and discount | Completed
|  |  | Mod3.1.3 | >> Uniform Fees and Discount | Completed
|  |  | Mod3.1.4 | >> Transportation Fees and discount | Completed
|  |  | Mod3.1.5 | >> Student Fees Types | Completed
|  |  | Mod3.1.6 | >> Student Payment Auto link with Financial | Completed
|  |  | Mod3.1.7 | >> Other Comments | Completed
|  |  | Mod3.1.8 | Student Payment Reports | In Progress
| Mod4 | Financial Module | Mod4.1 | Analysis | Completed
|  |  | Mod4.2 | Design | Completed
|  |  | Mod4.3 | Development | Completed
|  |  | Mod4.4 | Accounting Guide | Completed
|  |  | Mod4.4.1 | Assets أصول | Completed
|  |  | Mod4.4.2 | Discounts خصوم | Completed
|  |  | Mod4.4.3 | expenses مصروفات | Completed
|  |  | Mod4.4.4 | income ايرادات | Completed
|  | Accounting Details Forms | Mod4.5 | Accounting Tree (Add/Edit/Delete) | Completed
|  |  | Mod4.5.1 | Sub Accoutnig Tree (Add/Edit/Delete) | Completed
|  |  | Mod4.5.2 | Daily Jornal | Completed
|  |  | Mod4.5.3 | Ledger | Completed
|  |  | Mod4.5.4 | Trial Balance | Completed
|  |  | Mod4.5.5 | Recive statements | Completed
|  |  | Mod4.5.6 | BankDeposit ,Withdrow | Completed
|  |  | Mod4.5.7 | Permission for cash Debit ,Credit | Completed
|  |  | Mod4.5.8 | Cost centers / Reports | Completed
|  |  | Mod4.5.9 | Account statement | Completed
|  |  | Mod4.5.10 | Main treasury | Completed
|  |  | Mod4.5.11 | Sub Treasury | Completed
|  |  | Mod4.5.12 | Treasury Reports | Completed
|  |  | Mod4.5.13 | Expenses | Completed
|  |  | Mod4.5.14 | Expenses Registration | Completed
|  |  | Mod4.5.15 | Cash Recivable -payable | Completed
|  |  | Mod4.5.16 | Note Recivable -payable | Completed
|  |  | Mod4.5.17 | cheque Recivable -payable | Completed
|  |  | Mod4.5.18 | Dedecation & bonus | Completed
|  |  | Mod4.5.19 | income statement | Completed
|  |  | Mod4.5.20 | First Balance | Completed
|  |  | Mod4.5.21 | General Budget الميزانية | In Progress
|  |  | Mod4.5.22 | ميزان المراجعة | In Progress
|  |  | Mod4.5.23 |  | In Progress
|  |  | Mod4.5.24 | Expensex Reports | In Progress
|  |  | Mod4.5.25 | Journal -Entry Report | In Progress
|  |  | Mod4.5.26 | ledger account report | In Progress
|  |  | Mod4.5.27 | trial Palance report | In Progress
|  |  | Mod4.5.28 | receipt / exchange reports | In Progress
|  |  | Mod4.5.29 | account statement repoer | In Progress
|  |  | Mod4.5.30 | Treasury Reports | In Progress
|  |  | Mod4.5.31 | check deposit withdrow perort | In Progress
|  |  | Mod4.5.32 | visa transaction Report | In Progress
|  |  | Mod4.5.33 | Bus Expenses Report | In Progress
|  |  | Mod4.5.34 | Cost centers reports | In Progress
|  |  | Mod4.5.35 | Student Account ,payment Report | Completed
|  |  |  | TESTING | Completed
| Mod5 | HR Module | Mod5.0 | Analysis | Completed
|  |  | Mod5.1.1 | Employees | Completed
|  |  | Mod5.1.2 | Salary Types | Completed
|  |  | Mod5.1.3 | Employee Salary Config | Completed
|  |  | Mod5.1.4 | Bonus and Deduction Items | Completed
|  |  | Mod5.1.5 | Bonus and Deduction Form for add to Employee by month | Completed
|  |  | Mod5.1.6 | Monthly Salary | In Progress
ملفات العمل
|  |  | Mod5.2.1 | الأجازات واعداداتها | In Progress
|  |  | Mod5.2.2 | التأشيرات | In Progress
|  |  | Mod5.2.3 | الاجرااءت | In Progress
|  |  | Mod5.2.4 | التأمين الطبي | In Progress
|  |  | Mod5.2.5 | شركات الطيران - خطوط السفر | In Progress
|  |  | Mod5.2.6 | طلبات التوظيف | In Progress
|  |  | Mod5.2.7 | المرافقين | In Progress
|  |  | Mod5.2.8 | الايقافات | In Progress
المعاملات
|  |  | Mod5.3.1 | عقد موظف | In Progress
|  |  | Mod5.3.2 | مباشرة العمل | In Progress
|  |  | Mod5.3.3 | ترقية موظف | In Progress
|  |  | Mod5.3.4 | نقل موظف | In Progress
|  |  | Mod5.3.5 | هروب موظف | In Progress
|  |  | Mod5.3.6 | خروج ولم يعد | In Progress
|  |  | Mod5.3.7 | نقل كفالة | In Progress
|  |  | Mod5.3.8 | تجديد مستندات | In Progress
|  |  | Mod5.3.9 | اصابات عمل | In Progress
|  |  | Mod5.3.10 | سلف الموظفين | In Progress
|  |  | Mod5.3.11 | سداد جزء من السلفة | In Progress
|  |  | Mod5.3.12 | بدلات السكن | In Progress
|  |  | Mod5.3.13 | ايقاف موظف | In Progress
|  |  | Mod5.3.14 | معاملات ايام التجاوز | In Progress
|  |  | Mod5.3.15 | استلام وثائق السفر | In Progress
|  |  | Mod5.3.16 | الخروج و العودة | In Progress
|  |  | Mod5.3.17 | طلبات الاجازة و جدولتها | In Progress
|  |  | Mod5.3.18 | صرف تذاكر سفر | In Progress
|  |  | Mod5.3.19 | تصفيات الموظفين | In Progress
|  |  | Mod5.3.20 | عهد الموظفين | In Progress
|  |  | Mod5.3.21 | التقارير | In Progress
|  |  |  | TESTING | In Progress
| Mod6 | Inventory Module | Mod6.0 | Analysis
ملفات العمل
|  |  | Mod6.1.1 | هيكلة و شجرة المخازن
|  |  | Mod6.1.2 | أنواع المخازن
|  |  | Mod6.1.2 | أرقام المخازن و بياناتها
|  |  | Mod6.1.3 | ارقام الاماكن بالمخازن
|  |  | Mod6.1.4 | ارقام مجموعات الاصناف
|  |  | Mod6.1.5 | ارقام الاصناف
|  |  | Mod6.1.6 | أرقام الخدمات
|  |  | Mod6.1.7 | أنواع الحركات على المخزن
|  |  | Mod6.1.8 | جهات صرف
المعاملات
Mod6.2
|  |  | Mod6.2.1 | ادخال رصيد افتتاحي للمخزن
|  |  | Mod6.2.2 | ادخال ارصدة الجرد
|  |  | Mod6.2.3 | تسوية الجرد
|  |  | Mod6.2.4 | ادخال الاصناف
|  |  | Mod6.2.5 | استلام المواد + سندات الاستلام + قيود الحركة
|  |  | Mod6.2.6 | أرجاع مواد + سندات الارجاع + قيود الحركة
|  |  | Mod6.2.7 | تحويل الاصناف بين المخازن + قيود الحركة
|  |  | Mod6.2.8 | استلام التحويل بين المخازن + قيود الحركة
|  |  | Mod6.2.9 | أرصدة المخازن
|  |  | Mod6.2.10 | ترحيل حركات المخازن و قيود الحركات و التسميع بالحسابات
|  |  | Mod6.2.11 | الباركود للاصناف و الطباعة و التعريفات له بالنظام
Mod6.2.12
|  | التقارير | Mod6.2.13 | تقارير المخازن و الحركات و الارصدة
|  |  |  | TESTING | In Progress
Note on A7: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B7: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C7: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on E7: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on F7: • Status: This column should be populated with the current status of the functional requirement.
Note on G7: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on H7: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on I7: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
Note on F72: Hany: