## Requirement_Traceability_Matrix
CAMPUS SMART TECHNOLOGY
REQUIREMENTS TRACEABILITY MATRIX
Project Name: |  | Campus Smart ERP
National Center: |  | <required>
Project Manager Name: |  | Hany Shebl
Project Description: |  | Develop a full ERP system
|  | BRD |  | FSD
ID | Business Requirement ID# | Business Requirement / Business Use case | Functional Requirement ID# | Functional Requirement// Detail | Development Status | Tested In | Implemented In | Verification | Additional Comments
001 | Mod1 | Basic Forms Module | Mod1.1 | Company Form (Add/Edit/Delete) | Completed
002 |  |  | Mod1.2 | Branches Form (Add/Edit/Delete) | Completed
003 |  |  | Mod1.3 | Years Form (Add/Edit/Delete) | Completed
004 |  |  | Mod1.4 | Countries Form (Add/Edit/Delete) | Completed
005 |  |  | Mod1.5 | City Form (Add/Edit/Delete) | Completed
008 |  |  |  | Banks Form (Add/Edit/Delete) | Completed
009 |  |  |  | Bank Branches Form (Add/Edit/Delete) | Completed
010 |  |  |  | Bank Accounts Form (Add/Edit/Delete) | Completed
011 |  |  |  | School Form (Add/Edit/Delete) | Completed
012 |  |  |  | Stages Form (Add/Edit/Delete) | Completed
013 |  |  | Mod1 Testing |  | In Progress
014
015 | Mod2 | Bus Module | Mod2.1 | Bus Main info Form (Add/Edit/Delete) | Completed
016 |  |  | Mod2.2 | Bus Ways Form (Add/Edit/Delete) | Completed
017 |  |  | Mod2.3 | Bus Drivers Form (Add/Edit/Delete) | Completed
018 |  |  | Mod2.4 | Bus Price List Form (Add/Edit/Delete) | Completed
019 |  |  | Mod2.5 | Bus Discounts Form (Add/Edit/Delete) | Completed
018 |  |  | Mod2.6 | Bus Complains and Monitoring Form | In Progress
018 |  |  | Mod2.8 | Bus Reports | In Progress
020 |  |  | Mod1 Testing |  | In Progress
021
022 | Mod3 | Student Registeration | Mod3.1 | Student info & Img Form (Add/Edit/Delete) | Completed
023 |  |  | Mod3.1 | Student Configuration Form | Testing
024 |  |  | Mod3.1.1 | >> Main Fees and discount | In Progress
025 |  |  | Mod3.1.2 | >> Books Fees and discount | In Progress
026 |  |  | Mod3.1.3 | >> Uniform Fees and Discount | In Progress
027 |  |  | Mod3.1.4 | >> Transportation Fees and discount | In Progress
028 |  |  | Mod3.1.5 | >> Other Comments | In Progress
029
022 | Mod4 | Financial Module | Mod4.1 | Analysis | In Progress
|  |  | Mod4.2 | Design | In Progress
|  |  | Mod4.3 | Development | In Progress
|  |  | Mod4.4 | Accounting Guide
|  |  | Mod4.4.1 | Assets Form (Add/Edit/Delete)
|  |  | Mod4.4.2 | Discounts Form (Add/Edit/Delete)
|  |  | Mod4.4.3 | expenses Form (Add/Edit/Delete)
|  |  | Mod4.4.4 | income Form (Add/Edit/Delete)
Mod4.4.4
Mod4.4.4
Mod4.4.4
Mod4.4.4
Mod4.4.4
Mod4.4.4
Mod4.4.4
Mod4.4.4
Mod4.4.4
022 | Mod5 | HR Module | Mod5.1 | Analysis | In Progress
022 | Mod6 | Inventroy Module | Mod6.1 | Analysis | In Progress
031
032
033
034
Note on A8: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B8: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C8: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on E8: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on F8: • Status: This column should be populated with the current status of the functional requirement.
Note on G8: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on H8: • Implemented In: This column should be populated with the module that the functional requirement has been implemented in.
Note on I8: • Verification: This column should be populated with a description of the verification document linked to the functional requirement.